## Sheet1
Prod Line | Project ID | Project Name | JIT/ Dis/ Subtask | Parent Project ID | Global Practice | Practice Manager | TL Name | Country Name | Req Unit | Resp Unit | AIS Sign-off | Concept Review |  | Mgmt. Approval of Concept * |  | AIS Sign off to Cncpt Note Appr (Mths) | Decision Review |  | Mgmt Endor. Of Delivery * |  | Mgmt. Appr of CN to Mgmt. Endor. of.Del (Mths) | Final Del./ Completion Summary * |  | Mgmt. Appr of CN to Fin.Del. Cmpl Sum. (Mths) | Mgmt. End of Del. to Fin.Del. Cmpl Sum. (Mths) | Curr FY Actuals BB/ Reimb. ($k) | Curr FY Actuals TF ($k) | Curr FY Actuals BB/ Reimb.+TF ($k) | Total Actuals BB/ Reimb. ($k) | Total Actuals TF ($k) | Total Actuals BB/ Reimb. +TF ($k)
Trade & Cmptitvnss |  | 202 | [9 empty] | 122 |  | 121 |  |  | 66 |  | 69 |  |  | 81 |  |  |  | 7136.5904 | 7291.4326 | 14428.023 | 28139.9056 | 41644.7997 | 69784.7053
TA | P128148 | SD: Follow up Investment Climate Issues | D |  | Trade & Cmptitvnss | RASAGAM | Christow,Dobromir | Sudan | AFCE4 | GTCDR | 09/07/11 | 10/17/11 | A | 04/23/13 | A | 19 | 09/10/14 | A | 10/21/14 | A | 17 | 01/01/15 | A | 20 | 2 | 20.4323 |  | 20.4323 | 241.2252 |  | 241.2252
PA | P147505 | CA Quality for Competitiveness | NA |  | Trade & Cmptitvnss | ANOS CASERO | Salinas Munoz,Emanuel | Central Asia | ECCU8 | GTCDR | 09/06/13 | 09/30/13 | A | 10/03/13 | A | 0 |  |  | NA |  |  | 01/03/15 | A | 15 |  |  |  |  | 86.3766 |  | 86.3766
TA | P130208 | 6R Caribbean Forum | D |  | Trade & Cmptitvnss | MOTTA | Gallina,Andrea | Caribbean | LCC3C | GTCDR | 02/10/12 | 01/28/13 | A | 10/28/14 | A | 32 | 11/10/14 | A | 11/17/14 | A | 0 | 01/08/15 | A | 2 | 1 |  |  |  | 503.6842 |  | 503.6842
TA | P143436 | PPP: Capacity Building | J |  | Trade & Cmptitvnss | SPEAKMAN | Speakman,John F. | Congo, Republic of | AFCC2 | GTCDR | 12/05/12 | NA |  | NA |  | NA | NA |  | NA |  |  | 01/19/15 | A | 25 | 9 |  |  |  |  | 72.1979 | 72.1979
TA | P153752 | Jamaican Logistic Hub | J |  | Trade & Cmptitvnss | KOUAME | Djiofack,Calvin Zebaze | Jamaica | LCC3C | GMFDR | 12/01/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 01/20/15 | A | 1 | 0
TA | P132935 | CV: Increasing Linkages - Institutions | D |  | Trade & Cmptitvnss | SPEAKMAN | Garcia,Andres F. | Cabo Verde | AFCF1 | GTCDR | 09/13/12 | 03/12/13 | A | 09/17/13 | A | 12 | 01/16/15 |  | 12/20/14 | A | 15 | 01/22/15 | A | 16 | 1 | 5.4215 |  | 5.4215 | 151.2767 |  | 151.2767
TA | P125104 | ZW:Trade & Trans. Facilitation Zimbabwe | D |  | Trade & Cmptitvnss | RASAGAM | Mtonya,Brian G. | Zimbabwe | AFCS3 | GTCDR | 01/12/11 | 05/31/11 | A | 04/02/13 | A | 26 | 11/14/14 | A | 12/15/14 | A | 20 | 01/23/15 | A | 21 | 1 |  | 27.1565 | 27.1565 | 0.225 | 343.522 | 343.747
KP | P131008 | Trade policy and food security | D |  | Trade & Cmptitvnss | SAEZ | Gillson,Ian John Douglas | World | GTCDR | GTCDR | 03/06/12 | 04/30/12 | A | [8 empty] | 01/27/15 | A |  |  | 16.7756 |  | 16.7756 | 101.4488 | 3.0125 | 104.4613
TA | P151570 | Advice on Nat'l Quality Infrastructure | Subtask | P147060 | Trade & Cmptitvnss | ANOS CASERO | Rekas,Melissa | Belarus | ECCU2 | ECSPF - HIS | 07/10/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 01/28/15 | A | 6
TA | P151571 | Advice on Minority Shareholders' Rights | Subtask | P147060 | Trade & Cmptitvnss | ANOS CASERO | Rekas,Melissa | Belarus | ECCU2 | ECSPF - HIS | 07/10/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 01/28/15 | A | 6
KP | P133092 | FIEEI Product Briefs | D |  | Trade & Cmptitvnss | TILMES | Mogollon,Maria Paulina | Multi-Regional | FIEEI - HIS | GTCDR | 09/14/12 | 09/07/12 | [9 empty] | 01/29/15 | A |  |  | 11.7878 |  | 11.7878 | 128.1106 |  | 128.1106
EW | P133659 | Lao PDR ICA 2014 Update | D |  | Trade & Cmptitvnss | HADDAD | Record,Richard James Lowden | Lao People's Democratic Republic | EACTF | GTCDR | 10/01/12 | 11/07/13 | A | 11/25/13 | A | 13 | 11/07/14 | A | 11/24/14 | A | 11 | 02/08/15 | A | 14 | 2 | 24.0948 |  | 24.0948 | 71.1833 |  | 71.1833
TA | P146939 | 6C Trade and Logistics | D |  | Trade & Cmptitvnss | KOUAME | Koehler-Geib,Friederike N. | Central America | LCC2C | GMFDR | 07/31/13 | 10/29/13 | A | 07/11/14 | A | 11 |  |  | 12/22/14 | A | 5 | 02/08/15 | A | 6 | 1 | 3 | 0.72 | 3.72 | 126.7016 | 0.72 | 127.4216
TA | P147207 | CR Integration into Global Value Chains | D |  | Trade & Cmptitvnss | MOTTA | Kenyon,Thomas | Costa Rica | LCC2C | GTCDR | 09/30/13 | 12/10/13 | A | 01/02/14 | A | 3 | 09/10/14 | A | 10/07/14 | A | 9 | 02/14/15 | A | 13 | 4 | 22.7836 |  | 22.7836 | 147.2024 |  | 147.2024
TA | P150107 | Investment Policy - Caribbean Region | J |  | Trade & Cmptitvnss | MOTTA | Shahidsaless,Raha | Caribbean | LCC3C | GTCDR | 02/25/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 02/22/15 | A | 11 | 0 |  |  |  | 77.8147 |  | 77.8147
TA | P126448 | Zimbabwe Small Business Survey | D |  | Trade & Cmptitvnss | RASAGAM | Mtonya,Brian G. | Zimbabwe | AFCS3 | GTCDR | 05/09/11 | 05/12/11 | A | 12/28/12 | A | 19 | 10/21/13 | A | 04/16/14 | A | 15 | 02/23/15 | A | 25 | 10 |  | 31.895 | 31.895 |  | 519.2822 | 519.2822
TA | P128026 | ZA Economic Diversificaiton and MSME Dev | D |  | Trade & Cmptitvnss | RASAGAM | Mengistae,Taye Alemu | South Africa | AFCS1 | GTCDR | 09/07/11 | 07/26/11 | A | 08/01/11 | A | -1 | 04/03/14 | A | 02/05/15 | A | 42 | 02/28/15 | A | 42 | 0 | 32.1884 |  | 32.1884 | 543.1453 |  | 543.1453
IE | P143287 | Female Entrepreneurship Pilots IE | D |  | Trade & Cmptitvnss | TILMES | Iacovone,Leonardo | Africa | FIEEI - HIS | GTCDR | 10/18/12 | 01/22/15 |  |  |  |  | 02/25/15 |  |  |  |  | 03/03/15 |  |  |  | 4.523 |  | 4.523 | 5.3582 |  | 5.3582
EW | P145045 | Subnational Doing Business in Mexico V | D |  | Trade & Cmptitvnss | MOTTA | Salgado Otonel,Pilar | Mexico | LCC1C | GTCDR | 03/05/13 | 04/22/13 | A | 04/23/13 | A | 1 | 04/09/14 | A | 04/16/14 | A | 11 | 03/09/15 | A | 22 | 10 | 2.1106 |  | 2.1106 | 239.2617 |  | 239.2617
TA | P115090 | MDTF to Improve Investment Climate | D |  | Trade & Cmptitvnss | HADDAD | Temenggung,Della Y.A. | Indonesia | EACIF | GTCDR | 12/18/08 | 12/19/08 | A | 02/28/13 | A | 50 | 02/10/15 | A | 02/13/15 | A | 23 | 03/09/15 | A | 24 | 0 |  |  |  | 18.315 | 2293.9428 | 2312.2579
TA | P123351 | SC-PSD Reforms | D |  | Trade & Cmptitvnss | RASAGAM | Dimitriyev,Steven R. | Seychelles | AFCS2 | GTCDR | 12/14/10 | 12/05/11 | A | 02/19/13 | A | 26 | 03/29/13 | A | 04/29/13 | A | 2 | 03/09/15 | A | 24 | 22 | 31.8799 |  | 31.8799 | 231.8583 |  | 231.8583
TA | P144878 | Nature Conservancies Joint Ventures | J |  | Trade & Cmptitvnss | RASAGAM | Messerli,Hannah R. | Namibia | AFCS1 | GTCDR | 05/07/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 03/11/15 | A | 22 | 0 |  |  |  | 0.96646 | 22.9465 | 23.9129
TA | P114255 | IQ - Private Sector Development TA | D |  | Trade & Cmptitvnss | BENHASSINE | Dabidian,Hooman | Iraq | MNC02 | GTCDR | 02/09/09 | 10/19/09 | A | 10/14/09 | A | 8 | 01/28/10 | A | 10/29/14 | A | 60 | 03/13/15 | A | 64 | 4 |  | 32.2332 | 32.2332 | 265.0579 | 11311.3396 | 11576.3976
EW | P146683 | Caribbean New Trade Environment | D |  | Trade & Cmptitvnss | MOTTA | Djiofack,Calvin Zebaze | Caribbean | LCC3C | GTCDR | 08/12/13 | 10/01/13 | A | 03/07/14 | A | 6 | 12/22/14 | A | 01/05/15 | A | 9 | 03/22/15 | A | 12 | 2 | 1.6202 | 8.758 | 10.3782 | 70.7213 | 83.1664 | 153.8877
TA | P144860 | PPP Process, Pipeline, and Cap. building | D |  | Trade & Cmptitvnss | SPEAKMAN | Laure,Alexandre Hugo | Sierra Leone | AFCW1 | GTCDR | 02/26/13 | 04/29/13 | A | 04/29/13 | A | 2 | 03/14/14 | A | 09/04/14 | A | 16 | 03/22/15 | A | 22 | 6 |  | 58.1781 | 58.1781 |  | 225.6422 | 225.6422
TA | P130961 | Building Competitive Green Industries | D |  | Trade & Cmptitvnss | TILMES | Ehst,Michael | World | GTCID | GTCID | 03/08/12 | 12/12/12 | A | 12/30/12 | A | 9 | 05/15/14 | A | 02/15/15 | A | 25 | 03/22/15 | A | 26 | 1 |  | 0 | 0 |  | 475.8648 | 475.8648
TA | P145855 | ZAMBIA MINING LOCAL CONTENT PROGRAM | J |  | Trade & Cmptitvnss | RASAGAM | Mtonya,Brian G. | Zambia | AFCS3 | GTCDR | 07/24/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 03/22/15 | A | 19 | 3 |  |  |  | 113.5917 |  | 113.5917
TA | P130700 | GA Econ Diversification RTA | D |  | Trade & Cmptitvnss | SPEAKMAN | de Barros,Gilberto | Gabon | AFCC1 | GTCDR | 02/08/12 | 05/10/13 | A | 10/20/13 | A | 20 | 09/10/14 | A | 09/17/14 | A | 10 | 03/23/15 | A | 17 | 6 |  |  |  | 365.2062 |  | 365.2062
KP | P128815 | Service Export Competitiveness |  |  | Trade & Cmptitvnss | SAEZ | Saez,Juan Sebastian | World | GTCDR | GTCDR | 10/03/11 | 03/22/12 | A | [8 empty] | 03/24/15 | A |  |  | 18.8138 | 5.06 | 23.8738 | 344.8781 | 29.06 | 373.9381
TE | P123836 | AFR 9 Know-how in Southern Africa |  |  | Trade & Cmptitvnss | RASAGAM | Muradyan,Sofya | Africa | AFRVP | GTCDR | 08/23/10 |  | A | 08/20/10 | A | 0 | [5 empty] | 03/26/15 | A | 55 | [5 empty] | 708.2977 | 708.2977
EW | P132930 | Fostering Competitiveness and Growth | D |  | Trade & Cmptitvnss | RASAGAM | Fine,Gary J. | South Sudan | AFCE4 | GTCDR | 10/03/12 | 01/18/13 | A | 01/19/13 | A | 3 | 06/05/14 | A | 12/23/14 | A | 23 | 03/30/15 | A | 26 | 3 | 21.6995 |  | 21.6995 | 187.0333 |  | 187.0333
TA | P147229 | 6C Doing Business in Central America | Subtask | P145170 | Trade & Cmptitvnss | MOTTA | Bustelo,Federico Matias | Central America | LCC2C | GTCDR | 09/02/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 03/30/15 | A | 18 |  | 15.0502 | 35.3704 | 50.4206 | 45.0517 | 164.8792 | 209.9309
TA | P149915 | LC RAS St Lucia PPP Policy | J |  | Trade & Cmptitvnss | MOTTA | Briceno-Garmendia,Cecilia M. | St. Lucia | LCC3C | GTCDR | 02/25/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 03/30/15 | A | 13 |  | 33.2179 |  | 33.2179 | 33.2179 |  | 33.2179
TA | P150778 | Investment Promotion Assessment | J |  | Trade & Cmptitvnss | MOTTA | Espinosa-Wang,Alejandro | Trinidad and Tobago | LCC3C | GTCDR | 04/24/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 03/30/15 | A | 11 | 2 | 44.9592 |  | 44.9592 | 44.9592 |  | 44.9592
EW | P131936 | Logistics in Lagging Regions | D |  | Trade & Cmptitvnss | SAEZ | Kunaka,Charles | World | GTCDR | GTCDR | 07/25/12 | 01/30/14 | A | 06/30/14 | A | 23 | 02/13/15 |  | 03/31/15 | A | 9 | 03/31/15 |  | 9 | 0 | 87.0208 | 21.402 | 108.4228 | 376.5057 | 355.5063 | 732.012
EW | P133304 | Ghana Competitiveness and Job Creation | D |  | Trade & Cmptitvnss | SPEAKMAN | Issa,Djibrilla Adamou | Ghana | AFCW1 | GTCDR | 09/10/12 | 11/29/12 | A | 11/29/12 | A | 2 | 03/09/15 | A | 03/30/15 | A | 28 | 03/31/15 |  | 28 | 0 | 19.1878 | 44.8526 | 64.0405 | 267.4097 | 247.7378 | 515.1475
EW | P143595 | Myanmar ICA | D |  | Trade & Cmptitvnss | HADDAD | Spreng,Connor P. | Myanmar | EACTF | GTCDR | 10/29/12 | 09/13/12 | A | 11/09/12 | A | 0 | 11/25/14 | A | 01/27/15 | A | 26 | 03/31/15 |  | 28 | 2 | 101.2298 |  | 101.2298 | 363.4781 |  | 363.4781
TA | P115576 | KH-Technical Assistance to TRAC | D |  | Trade & Cmptitvnss | HADDAD | Clarke,Julian Latimer | Cambodia | EACTF | GTCDR | 01/07/09 | 03/02/11 | A | 03/11/11 | A | 26 | 03/30/15 | A | 02/27/15 |  | 47 | 03/31/15 |  | 48 | 1 |  | 632.9987 | 632.9987 |  | 2991.4311 | 2991.4311
TA | P150741 | Indicator Based Reform Advisory | J |  | Trade & Cmptitvnss | MOTTA | Franco-Temple,Ernesto | Uruguay | LCC7C | GTCDR | 04/24/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 03/31/15 |  | 11 | 0 | 13.1214 |  | 13.1214 | 16.1682 |  | 16.1682
TA | P121810 | NG - Trade Facilitation and Policy Proj | D |  | Trade & Cmptitvnss | SPEAKMAN | Buba,Johanne | Nigeria | AFCW2 | GTCDR | 05/06/10 | 11/27/13 | A | 03/10/15 | A | 58 | 03/18/15 |  | 03/13/15 | A | 0 | 04/06/15 | A | 0 | 0 | 0.16478 | 0 | 0.16478 | 82.7122 | 608.945 | 691.6572
EW | P143446 | Support to SACU Secretariat | D |  | Trade & Cmptitvnss | RASAGAM | Farole,Thomas | Africa | AFCRI | GTCDR | 02/11/13 | 02/08/13 |  | 10/10/13 | A | 7 | 12/12/14 | A | 02/25/15 | A | 16 | 04/10/15 |  | 18 | 1 |  | 196.2375 | 196.2375 | 53.6186 | 314.1237 | 367.7423
EW | P132874 | Sierra Leone Growth Pole Diagnostic | D |  | Trade & Cmptitvnss | SPEAKMAN | Laure,Alexandre Hugo | Sierra Leone | AFCW1 | GTCDR | 08/08/12 | 11/06/12 | A | 11/20/12 | A | 3 | 07/17/13 | A | 11/05/13 | A | 11 | 04/10/15 |  | 28 | 17 | 61.4698 | 421.7828 | 483.2526 | 367.6403 | 977.5179 | 1345.1582
TA | P125402 | Staff Support to TFF Activities | D |  | Trade & Cmptitvnss | SAEZ | Haddad,Mona E. | World | GTCDR | GTCDR | 01/06/11 | 12/23/10 |  | 03/27/15 | A | 50 |  |  | 03/31/15 | A | 0 | 04/13/15 | A | 0 | 0 |  | 242.8944 | 242.8944 |  | 1563.669 | 1563.669
TA | P132218 | Trade in Agricultural Markets (TFF) | D |  | Trade & Cmptitvnss | SPEAKMAN | Gurcanlar,Tugba | Nigeria | AFCW2 | GTCDR | 08/20/12 | 11/15/12 | A | 02/04/13 | A | 5 | 12/09/14 | A | 01/28/15 | A | 23 | 04/13/15 | A | 26 | 2 |  | 501.7054 | 501.7054 |  | 1158.2279 | 1158.2279
EW | P145785 | Dominican Republic Trade Diagnostic | D |  | Trade & Cmptitvnss | MOTTA | Sanchez Martin,Miguel Eduardo | Dominican Republic | LCC3C | GTCDR | 05/08/13 | 11/05/13 | A | 11/26/13 | A | 6 | 06/17/14 | A | 06/30/14 | A | 7 | 04/14/15 | A | 16 | 9 |  | 25.7266 | 25.7266 |  | 96.6669 | 96.6669
EW | P147941 | Inclusive Markets | D |  | Trade & Cmptitvnss | SPEAKMAN | Buba,Johanne | Nigeria | AFCW2 | GTCDR | 09/20/13 | 11/20/13 | A | 12/17/13 | A | 2 | 06/30/14 | A | 04/10/15 |  | 15 | 04/16/15 |  | 15 | 0 | 37.7431 |  | 37.7431 | 74.7451 |  | 74.7451
TA | P131158 | Compet Policy & IBRA | Subtask | P145170 | Trade & Cmptitvnss | MOTTA | Espinosa-Wang,Alejandro | Latin America | GTCDR | GTCDR | 03/30/12 | NA |  | NA |  | NA | NA |  | NA |  | 58 | 04/24/15 |  | 36 | -22 | 6.3952 | 159.5899 | 165.9851 | 15.8022 | 1191.1217 | 1206.924
EW | P150486 | LY: Trade Integration | J |  | Trade & Cmptitvnss | BENHASSINE | Malouche,Mariem | Libya | MNC01 | GTCDR | 05/21/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 04/30/15 |  | 11 | 7 |  |  |  | 4.3522 |  | 4.3522
KP | P146254 | CI KP Implementation | D |  | Trade & Cmptitvnss | SAGER | Kassim,Suhail | World | GTCDR | GTCDR | 06/13/13 | 08/08/13 | A | 05/12/14 | A | 10 | 10/08/14 | A | 03/11/15 | A | 9 | 04/30/15 |  | 11 | 1 |  | 66.5307 | 66.5307 |  | 374.3128 | 374.3128
TA | P133061 | Multi-sector Sources of Growth | D |  | Trade & Cmptitvnss | SPEAKMAN | Marchat,Jean Michel Noel | Gambia, The | AFCF1 | GTCDR | 09/28/12 | 12/12/13 | A | 01/08/14 | A | 15 | 01/15/15 | A | 02/09/15 | A | 13 | 04/30/15 |  | 15 | 2 | 37.6025 |  | 37.6025 | 170.5582 |  | 170.5582
TA | P149337 | Khanty-Mansiysk Gas Cluster Development | Subtask | P145769 | Trade & Cmptitvnss | ANOS CASERO | Haven,Thomas Edward | Russian Federation | ECCU1 | GTCDR | 12/30/13 | NA |  | NA |  | NA | NA |  | NA |  | 11 | 04/30/15 |  | 16 | 3 | 108.0796 |  | 108.0796 | 108.0796 |  | 108.0796
TA | P146914 | Comesa Customs Union - CTN and CMR | D |  | Trade & Cmptitvnss | RASAGAM | Hartmann,Olivier | Africa | AFCRI | GTCDR | 11/04/13 | 11/25/13 | A | 11/27/13 | A | 0 | 03/02/15 |  | 04/15/15 |  | 16 | 04/30/15 |  | 17 | 0 |  | 526.2145 | 526.2145 |  | 1397.0823 | 1397.0823
TA | P132682 | Southern African Dev Community Visa | J |  | Trade & Cmptitvnss | RASAGAM | Mateev,Eneida Fernandes | Southern Africa | AFCRI | GTCDR | 08/20/12 | NA |  | NA |  | NA | NA |  | NA |  |  | 04/30/15 |  | 32 | 0 |  | 341.071 | 341.071 |  | 1087.7642 | 1087.7642
TA | P152834 | PE Effectiveness of Competition Policy | Subtask | P145170 | Trade & Cmptitvnss | MOTTA | Martinez Licetti,Martha | Peru | LCC6C | GTCDR | 09/26/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 04/30/15 |  | 7 | 1 | 81.7022 |  | 81.7022 | 81.7022 |  | 81.7022
EW | P132559 | Regional Foodstaples Trade | D |  | Trade & Cmptitvnss | SPEAKMAN | Maur,Jean-Christophe | Western Africa | AFCRI | GTCDR | 08/29/12 | 12/18/12 | A | 12/13/13 | A | 15 | 11/15/14 | A | 04/24/15 |  | 16 | 05/01/15 |  | 16 | 0 | 59.5955 | 85.1326 | 144.7281 | 136.5844 | 556.9457 | 693.5301
RF | P130381 | Measuring the Efficiency of Markets | D |  | Trade & Cmptitvnss | SPEAKMAN | Gonzalez,Alvaro S. | Africa | GTCDR | GTCDR | 01/26/12 | 01/18/12 | A | [8 empty] | 05/01/15 |  |  |  | 50.1213 |  | 50.1213 | 99.4827 |  | 99.4827
TA | P148016 | Tourism Sector Note | D |  | Trade & Cmptitvnss | SPEAKMAN | Mateev,Eneida Fernandes | Guinea | AFCF2 | GTCDR | 09/25/13 | 11/29/13 | A | 04/30/14 | A | 7 | 04/17/15 |  | 04/20/15 |  | 11 | 05/01/15 |  | 12 | 0 | 11.2541 |  | 11.2541 | 42.331 |  | 42.331
TA | P147359 | Productivity, Innovation and IC Reform | D |  | Trade & Cmptitvnss | MOTTA | Rubalcaba Bermejo,Luis | Ecuador | LCC6C | GTCDR | 08/27/13 | 01/16/14 | A | 02/11/14 | A | 5 | 12/15/14 | A | 02/23/15 | A | 12 | 05/04/15 |  | 14 | 2 | 111.0208 |  | 111.0208 | 306.082 |  | 306.082
TA | P131824 | RAS-MAP-Competition Council | D |  | Trade & Cmptitvnss | ANOS CASERO | Aprahamian,Arabela Sena | Romania | ECCU5 | GTCDR | 05/23/12 | 05/30/12 | A | 06/05/12 | A | 0 | 05/21/12 | A | 04/20/15 |  | 34 | 05/06/15 |  | 35 | 0 | 219.1567 |  | 219.1567 | 1832.2757 |  | 1832.2757
EW | P144611 | SD: PromotingPrivateSectorRevitalization | D |  | Trade & Cmptitvnss | RASAGAM | Garcia,Andres F. | Sudan | AFCE4 | GTCDR | 03/07/13 | 10/14/13 | A | 10/14/13 | A | 7 | 04/10/15 |  | 04/17/15 |  | 18 | 05/08/15 |  | 18 | 0 | 6.6009 |  | 6.6009 | 22.3692 | 97.7103 | 120.0794
TA | P131782 | PSD Strategy & Dialogue | D |  | Trade & Cmptitvnss | SPEAKMAN | Fine,Gary J. | Liberia | AFCW1 | GTCDR | 09/04/12 | 11/30/12 | A | 12/06/12 | A | 3 | 12/18/14 | A | 04/10/15 |  | 28 | 05/08/15 |  | 29 | 0 | 83.5168 | 2.8 | 86.3168 | 332.9947 | 399.541 | 732.5357
EW | P147940 | Drivers of Jobs & Growth ICA | D |  | Trade & Cmptitvnss | SPEAKMAN | Buba,Johanne | Nigeria | AFCW2 | GTCDR | 09/20/13 | 11/20/13 | A | 12/17/13 | A | 2 | 03/30/15 |  | 04/09/15 |  | 15 | 05/15/15 |  | 16 | 1 | 29.8656 |  | 29.8656 | 32.8894 |  | 32.8894
PA | P147060 | Programmatic PSD TA | NA |  | Trade & Cmptitvnss | ANOS CASERO | Grigorian,Karen | Belarus | ECCU2 | GTCDR | 08/13/13 | 10/29/13 | A | 11/06/13 | A | 2 |  |  | NA |  |  | 05/15/15 |  | 18 |  | -0.1515 |  | -0.1515 | 137.4137 |  | 137.4137
PA | P145078 | NATL & REG INNO TA | NA |  | Trade & Cmptitvnss | ANOS CASERO | Kapil,Natasha | Poland | ECCU5 | GTCDR | 02/25/13 | 03/19/13 | A | 03/28/13 | A | 1 |  |  | NA |  |  | 05/15/15 |  | 25 |  |  |  |  | 0.59451 |  | 0.59451
TA | P147373 | Russia Post WTO Accession TA | D |  | Trade & Cmptitvnss | ANOS CASERO | Hansl,Birgit | Russian Federation | ECCU1 | GTCDR | 08/30/13 | 12/13/13 | A | 01/17/14 | A | 4 | 04/30/15 |  | 05/07/15 |  | 15 | 05/15/15 |  | 15 | 0 | 41.9791 |  | 41.9791 | 119.5421 |  | 119.5421
TA | P145647 | Strengthening Namibia Competition Policy | D |  | Trade & Cmptitvnss | RASAGAM | Zhang,Chunlin | Namibia | AFCS1 | GTCDR | 05/21/13 | 12/13/12 | A | 11/21/13 | A | 6 | 03/31/15 |  | 04/15/15 |  | 16 | 05/15/15 |  | 17 | 1 |  |  |  | 53.5121 |  | 53.5121
TA | P147308 | Competition Reform in Tabasco State | Subtask | P146293 | Trade & Cmptitvnss | MOTTA | Martinez Licetti,Martha | Mexico | LCC1C | GTCDR | 08/15/13 | 11/20/13 | A | 12/06/13 | A | 3 | 04/03/15 | A | 04/20/15 |  | 16 | 05/15/15 |  | 17 | 0 | 52.6632 |  | 52.6632 | 99.7866 |  | 99.7866
TA | P133750 | Caribbean Public-Private Dialogues | Subtask | P144730 | Trade & Cmptitvnss | MOTTA | Niang,Cecile Thioro | Caribbean | LCC3C | GTCDR | 09/23/12 | NA |  | NA |  | NA | NA |  | NA |  | 14 | 05/15/15 |  | 31 | 12 | 163.4618 |  | 163.4618 | 683.3383 |  | 683.3383
TA | P151630 | Regulatory policy capacity building | J |  | Trade & Cmptitvnss | ANOS CASERO | Gonzalez,Alvaro S. | Russian Federation | ECCU1 | GTCDR | 09/10/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 05/15/15 |  | 8
TA | P122849 | Belarus Privatization | D |  | Trade & Cmptitvnss | ANOS CASERO | Segal,Tatiana | Belarus | ECCU2 | GTCDR | 07/20/10 | 08/12/10 | A | 08/20/10 | A | 1 |  |  | 04/27/15 |  | 56 | 05/18/15 |  | 56 | 0 | 82.7142 |  | 82.7142 | 688.8565 |  | 688.8565
TA | P119018 | CO Technology Extension | Subtask | P144510 | Trade & Cmptitvnss | MOTTA | Iacovone,Leonardo | Colombia | LCC1C | GTCDR | 07/28/11 | 02/21/12 | A | 03/17/12 | A | 7 |  |  | 04/20/15 |  | 37 | 05/22/15 |  | 38 | 1 | 93.9347 |  | 93.9347 | 383.6906 |  | 383.6906
TA | P145530 | Export Development Strategy Implement | D |  | Trade & Cmptitvnss | ANOS CASERO | Gyulumyan,Gohar | Armenia | ECCU3 | GTCDR | 05/07/13 | 09/13/13 | A | 09/28/13 | A | 4 | 04/20/15 |  | 04/20/15 |  | 18 | 05/26/15 |  | 19 | 1 |  | 62.8073 | 62.8073 | 0 | 64.1909 | 64.1909
TA | P152378 | SA Medinah Growth | D |  | Trade & Cmptitvnss | BENHASSINE | Mousley,Peter J. | Saudi Arabia | MNC02 | GTCDR | 09/10/14 | 03/15/15 | A | 03/15/15 | A | 6 | 03/18/15 | A | 03/18/15 | A | 0 | 05/27/15 |  | 2 | 2 | 63.9486 |  | 63.9486 | 63.9486 |  | 63.9486
EW | P149800 | Trade Facilitation and Intervention | D |  | Trade & Cmptitvnss | SPEAKMAN | Tchana Tchana,Fulbert | Congo, Republic of | AFCC2 | GTCDR | 02/05/14 | 02/12/14 | A | 03/21/14 | A | 1 | 04/24/15 |  | 05/05/15 |  | 13 | 05/29/15 |  | 14 | 0 |  | 262.1269 | 262.1269 |  | 452.0529 | 452.0529
KP | P154855 | Smart Specialization | D |  | Trade & Cmptitvnss | ANOS CASERO | Aprahamian,Arabela Sena | Croatia | ECCU5 | GTCDR | 02/24/15 |  |  | 04/15/15 |  | 1 |  |  | 05/15/15 |  | 1 | 05/29/15 |  | 1 | 0 | 18.82 |  | 18.82 | 18.82 |  | 18.82
KP | P147528 | Global Connectivity Datasets | D |  | Trade & Cmptitvnss | SAEZ | Arvis,Jean Francois | World | GTCDR | GTCDR | 09/26/13 | 10/04/13 | A | 06/30/14 | A | 9 | 03/06/15 |  | 03/13/15 |  | 8 | 05/29/15 |  | 10 | 2 | 110.1315 | 177.2704 | 287.4019 | 266.6761 | 177.2704 | 443.9465
PA | P144730 | LCC3C CGF and CIDA EFO/Analytical Work | NA |  | Trade & Cmptitvnss | MOTTA | Niang,Cecile Thioro | Caribbean | LCC3C | GTCDR | 01/29/13 | 01/28/13 | A | 03/20/13 | A | 1 |  |  | NA |  |  | 05/29/15 |  | 26 |  | 52.8844 |  | 52.8844 | 52.8844 |  | 52.8844
TA | P153231 | Initial Competition Assessment | D |  | Trade & Cmptitvnss | ANOS CASERO | Gonzalez,Alvaro | Bulgaria | ECCU5 | GTCDR | 10/24/14 | 11/18/14 | A | 12/03/14 | A | 1 | 04/08/15 | A | 04/24/15 |  | 4 | 05/29/15 |  | 5 | 1 | 75.5045 |  | 75.5045 | 75.5045 |  | 75.5045
TA | P132421 | HT Trade Facilitation | D |  | Trade & Cmptitvnss | MOTTA | Djiofack,Calvin Zebaze | Haiti | LCC8C | GTCDR | 10/12/12 | 08/13/13 | A | 03/05/14 | A | 16 | 05/10/15 |  | 05/21/15 |  | 14 | 05/29/15 |  | 14 | 0 |  | 299.4668 | 299.4668 | 2.0055 | 1104.9256 | 1106.9311
TA | P145200 | SZ: TFF Customs Modernization | D |  | Trade & Cmptitvnss | RASAGAM | Kilroy,Austin Francis Louis | Swaziland | AFCS1 | GTCDR | 03/29/13 | 05/13/13 | A | 06/26/13 | A | 2 | 05/04/15 |  | 05/11/15 |  | 22 | 05/29/15 |  | 23 | 0 | 22.8671 | 136.9684 | 159.8355 | 102.3571 | 405.0738 | 507.4309
TA | P147655 | Competition Policy Assessment | J |  | Trade & Cmptitvnss | RASAGAM | Begazo Gomez,Tania Priscilla | Rwanda | AFCE2 | GTCDR | 09/04/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 05/29/15 |  | 20 | 0 | 15.8085 |  | 15.8085 | 115.514 |  | 115.514
TA | P149316 | Jamaica JIT: Trade as Driver for Growth | J |  | Trade & Cmptitvnss | MOTTA | Shahidsaless,Raha | Jamaica | LCC3C | GTCDR | 12/20/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 05/29/15 |  | 17 | 0 |  | 22.8563 | 22.8563 |  | 52.0757 | 52.0757
EW | P145228 | Benin: DTIS Update | D |  | Trade & Cmptitvnss | SPEAKMAN | Maur,Jean-Christophe | Benin | AFCF2 | GTCDR | 04/02/13 | 04/10/14 |  | 08/26/14 | A | 16 | 10/24/14 | A | 04/30/15 |  | 8 | 05/31/15 |  | 9 | 1 |  |  |  |  | 112.7366 | 112.7366
EW | P149411 | RAS Business entry & Property Registry | Subtask | P149111 | Trade & Cmptitvnss | ANOS CASERO | Papahagi,Madalina G. | Poland | ECCU5 | DECSN | 01/08/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 05/31/15 |  | 16 |  | 64.7585 |  | 64.7585 | 130.7708 |  | 130.7708
EW | P149412 | RAS Construction Lic. & Enforce Contract | Subtask | P149111 | Trade & Cmptitvnss | ANOS CASERO | Papahagi,Madalina G. | Poland | ECCU5 | DECSN | 01/08/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 05/31/15 |  | 16 |  | 167.2702 |  | 167.2702 | 172.3016 |  | 172.3016
PA | P149111 | Subnational Doing Business in Poland I | NA |  | Trade & Cmptitvnss | ANOS CASERO | Papahagi,Madalina G. | Poland | ECCU5 | GTCDR | 12/04/13 | 12/11/13 | A | 12/13/13 | A | 0 |  |  | NA |  |  | 05/31/15 |  | 17 |  | 68.8832 |  | 68.8832 | 245.7351 |  | 245.7351
TA | P147382 | Competition reform in Mexico State | Subtask | P146293 | Trade & Cmptitvnss | MOTTA | Martinez Licetti,Martha | Mexico | LCC1C | GTCDR | 08/28/13 | 11/20/13 | A | 12/06/13 | A | 3 |  |  | 04/30/15 |  | 16 | 05/31/15 |  | 17 | 1 | 34.511 |  | 34.511 | 69.0501 |  | 69.0501
TA | P152118 | OECS Tourism Competitiveness | J |  | Trade & Cmptitvnss | MOTTA | Shahidsaless,Raha | OECS Countries | LCC3C | GTCDR | 07/23/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 05/31/15 |  | 10 | 1 | 138.1903 |  | 138.1903 | 138.1903 |  | 138.1903
EW | P147217 | Uganda Local Content Multi-Sector Study | D |  | Trade & Cmptitvnss | RASAGAM | Goffe,Valeriya | Uganda | AFCE1 | GTCDR | 08/19/13 | 03/20/14 | A | 06/29/14 | A | 10 | 12/17/14 | A | 02/22/15 | A | 7 | 06/01/15 |  | 11 | 3 | 80.0835 |  | 80.0835 | 157.5822 |  | 157.5822
TA | P147220 | Export Competitiveness and Innovation | D |  | Trade & Cmptitvnss | RASAGAM | Mogollon,Maria Paulina | Kenya | AFCE2 | GTCDR | 09/17/13 | 12/17/13 | A | 03/13/14 | A | 5 | 04/16/15 |  | 04/30/15 |  | 13 | 06/01/15 |  | 14 | 1 | 88.8346 | 382.9019 | 471.7365 | 104.9914 | 521.7457 | 626.7371
TA | P144416 | PPPs and Capital Markets Development | D |  | Trade & Cmptitvnss | SPEAKMAN | de Barros,Gilberto | Africa | AFCRI | GTCDR | 12/22/12 | 05/30/13 | A | 09/22/13 | A | 9 | 05/08/15 |  | 05/15/15 |  | 19 | 06/01/15 |  | 20 | 0 | 0.45 |  | 0.45 | 200.2219 | 29.7114 | 229.9333
TA | P153620 | AFCS1 Competitiveness Dialogue | J |  | Trade & Cmptitvnss | RASAGAM | Zhang,Chunlin | South Africa | AFCS1 | GTCDR | 12/01/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/01/15 |  | 6 | 0 | 118.6941 |  | 118.6941 | 118.6941 |  | 118.6941
EW | P145240 | Natural Resources Regional Integration | D |  | Trade & Cmptitvnss | SPEAKMAN | Isik,Gozde | Africa | AFCRI | GTCDR | 05/22/13 | 11/27/13 | A | 11/27/13 | A | 6 | 05/01/15 |  | 05/15/15 |  | 17 | 06/05/15 |  | 18 | 0 | 47.6753 | 120.3187 | 167.994 | 76.0218 | 153.9863 | 230.0081
EW | P133267 | Assessment of Mining | D |  | Trade & Cmptitvnss | SPEAKMAN | Campos,Francisco Moraes Leitao | Guinea | AFCF2 | GTCDR | 09/10/12 | 11/29/13 | A | 12/05/14 | A | 26 | 05/22/15 |  | 05/29/15 |  | 5 | 06/08/15 |  | 6 | 0 | -7.1471 |  | -7.1471 | 134.8963 |  | 134.8963
EW | P148926 | MA: Trade and Competitiveness | D |  | Trade & Cmptitvnss | BENHASSINE | Malouche,Mariem | Morocco | MNC01 | GTCDR | 12/11/13 | 12/31/14 |  | 04/30/15 |  | 16 | 05/13/15 |  | 05/27/15 |  | 0 | 06/10/15 |  | 1 | 0 | 12.0277 |  | 12.0277 | 103.2461 | 63.0895 | 166.3356
EW | P143263 | Investment Climate Strategy | D |  | Trade & Cmptitvnss | SPEAKMAN | Dimitriyev,Steven R. | Congo, Democratic Republic of | AFCC2 | GTCDR | 10/23/12 | 11/22/13 | A | 11/29/13 | A | 13 | 05/06/15 |  | 05/29/15 |  | 18 | 06/10/15 |  | 18 | 0 | 86.9438 |  | 86.9438 | 1050.7337 |  | 1050.7337
TA | P146554 | Nouadhibou Free Zone Support | D |  | Trade & Cmptitvnss | SPEAKMAN | Laure,Alexandre Hugo | Mauritania | AFCF1 | GTCDR | 08/12/13 | 11/18/13 | A | 01/06/14 | A | 4 | 11/03/14 | A | 04/10/15 |  | 15 | 06/10/15 |  | 17 | 2 | 82.8109 | 70.5233 | 153.3342 | 192.5069 | 199.3368 | 391.8437
TA | P143215 | MNXTA: 5M Early Stage Innovation TA | D |  | Trade & Cmptitvnss | BENHASSINE | Al Rowais,Sara | Middle East and North Africa | MNARS | GTCDR | 10/02/12 | 09/17/12 |  | 11/11/13 | A | 13 | 04/30/15 |  | 05/13/15 |  | 18 | 06/10/15 |  | 18 | 0 |  |  |  |  | 167.4674 | 167.4674
EW | P146857 | Political Economy of Trade Reforms | D |  | Trade & Cmptitvnss | RASAGAM | Brenton,Paul | Africa | AFCRI | GTCDR | 09/12/13 | 12/04/13 | A | 06/27/14 | A | 9 | 11/12/14 | A | 03/25/15 | A | 8 | 06/12/15 |  | 11 | 2 | 32.5554 | 61.6495 | 94.2048 | 98.976 | 185.3697 | 284.3457
EW | P147764 | West African Regional Trade Solutions | D |  | Trade & Cmptitvnss | SPEAKMAN | Isik,Gozde | Western Africa | AFCW1 | GTCDR | 10/18/13 | 11/11/13 | A | 11/27/13 | A | 1 | 05/01/15 |  | 05/01/15 |  | 17 | 06/12/15 |  | 18 | 1 | 16.1214 | 3.6292 | 19.7506 | 34.3374 | 37.1236 | 71.461
KP | P153999 | Competitiveness in the South Caucasus | D |  | Trade & Cmptitvnss | ANOS CASERO | Dhanani,Qahir | Caucasus | ECCU3 | GTCDR | 12/04/14 | 03/18/15 | A | 04/20/15 |  | 4 |  |  | 05/25/15 |  | 1 | 06/12/15 |  | 1 | 0 | 44.3726 |  | 44.3726 | 44.3726 |  | 44.3726
TA | P151595 | Sahel-TA Infrastructure Competitiveness | D |  | Trade & Cmptitvnss | SPEAKMAN | Laure,Alexandre Hugo | Niger | AFCW3 | GTCDR | 10/01/14 | 01/26/15 | A | 02/16/15 | A | 4 | 05/11/15 |  | 05/19/15 |  | 3 | 06/12/15 |  | 3 | 0 | 19.5431 |  | 19.5431 | 19.5431 |  | 19.5431
TA | P132991 | Manufacturing Plan Implementation 2 | D |  | Trade & Cmptitvnss | LASAGABASTER | Kamphuis,Bertine | India | SACIN | GTCDR | 09/05/12 | 12/04/12 | A | 12/06/12 | A | 3 | 05/06/15 |  | 05/20/15 |  | 29 | 06/12/15 |  | 30 | 0 | 98.4703 | 196.8478 | 295.3181 | 421.291 | 547.9517 | 969.2427
EW | P151778 | SC-PPP Outsourcing and PSD dialogue | D |  | Trade & Cmptitvnss | RASAGAM | Dimitriyev,Steven R. | Seychelles | AFCS2 | GTCDR | 09/04/14 | 01/28/15 |  | 02/28/15 | A | 5 |  |  | 06/01/15 |  | 3 | 06/15/15 |  | 3 | 0 | 11.9101 |  | 11.9101 | 11.9101 |  | 11.9101
EW | P146575 | ICT and Innovation Study | D |  | Trade & Cmptitvnss | TILMES | Manes,Eric David | Sri Lanka | SACSL | GTCDR | 07/22/13 | 12/09/13 | A | 01/16/14 | A | 5 | 06/02/14 | A | 04/20/15 |  | 15 | 06/15/15 |  | 16 | 1 | 45.3624 |  | 45.3624 | 211.3154 |  | 211.3154
EW | P146899 | West Africa Monetary Zone TTFA | D |  | Trade & Cmptitvnss | SPEAKMAN | Njinkeu,Dominique | Western Africa | AFCRI | GTCDR | 08/14/13 | 09/26/13 | A | 10/10/13 | A | 1 | 04/30/15 |  | 05/15/15 |  | 19 | 06/15/15 |  | 20 | 1 |  | 45.9348 | 45.9348 |  | 240.8698 | 240.8698
EW | P149483 | Competitive Cities in India | Subtask | P146415 | Trade & Cmptitvnss | LASAGABASTER | Kamphuis,Bertine | India | SACIN | GTCDR | 01/20/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/15/15 |  | 16 | 1 | 10.1842 |  | 10.1842 | 41.3833 |  | 41.3833
IE | P128397 | BR PSD Impact Evaluation |  |  | Trade & Cmptitvnss | MOTTA | Kondylis,Florence | Brazil | LCC5C | GTCDR | 10/11/11 | 12/06/11 | A |  |  |  | 03/31/15 |  |  |  |  | 06/15/15 | [6 empty] | 99.0217 |  | 99.0217
KP | P143687 | Trade and conflict | D |  | Trade & Cmptitvnss | SAEZ | Cali,Massimiliano | World | GTCDR | GTCDR | 11/06/12 | 01/15/13 | A | 01/30/14 | A | 14 |  |  | 03/31/15 |  | 14 | 06/15/15 |  | 16 | 2 | 9.7637 | 7.5383 | 17.302 | 126.2257 | 7.5383 | 133.764
TA | P147012 | Local Content in the Oil and Gas Sector | D |  | Trade & Cmptitvnss | RASAGAM | Dall'Olio,Andrea Mario | Tanzania | AFCE1 | GTCDR | 11/24/13 | 02/25/14 | A | 02/06/15 | A | 14 | 03/31/15 |  | 04/15/15 |  | 2 | 06/15/15 |  | 4 | 2 | 101.1868 | 85.6387 | 186.8255 | 209.0425 | 85.6387 | 294.6812
TA | P147326 | Promoting PPPs through Capacity Building | J |  | Trade & Cmptitvnss | SPEAKMAN | de Barros,Gilberto | Africa | AFCRI | GTCDR | 08/22/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/15/15 |  | 21 | 1 | 20.7479 |  | 20.7479 | 20.7479 | 72.374 | 93.1219
TA | P153474 | PL-Business Environment/Innovation | J |  | Trade & Cmptitvnss | ANOS CASERO | Piatkowski,Marcin | Poland | ECCU5 | GTCDR | 12/03/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/15/15 |  | 6 | 5 | 68.327 |  | 68.327 | 68.327 |  | 68.327
EW | P154246 | Understanding firm-level innovation | J |  | Trade & Cmptitvnss | TILMES | Cirera,Xavier | World | GTCDR | GTCDR | 01/13/15 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/16/15 |  | 5 | 4 | 25.1972 |  | 25.1972 | 25.1972 |  | 25.1972
TA | P143887 | SME Masterplan Implementation Support | D |  | Trade & Cmptitvnss | HADDAD | Alavi,Hamid R. | Malaysia | EACTF | GTCDR | 12/12/12 | 12/20/12 | A | 12/20/12 | A | 0 | 01/31/15 |  | 02/16/15 |  | 25 | 06/16/15 |  | 29 | 4 | 173.1602 |  | 173.1602 | 894.573 |  | 894.573
KP | P154248 | STI policies in the Post 2015 SDG | D |  | Trade & Cmptitvnss | TILMES | Correa,Paulo Guilherme | World | GTCDR | GTCDR | 03/11/15 | 02/20/15 |  | 02/23/15 |  | 0 | 05/26/15 |  | 06/08/15 |  | 3 | 06/17/15 |  | 3 | 0 | 4.8043 |  | 4.8043 | 4.8043 |  | 4.8043
PA | P151788 | DROP-CG PSD RAS | NA |  | Trade & Cmptitvnss | SPEAKMAN | Hayatou,Mohamadou S | Congo, Republic of | AFCC2 | GTCDR | 10/23/14 | 03/25/15 |  | 04/22/15 |  | 5 |  |  | NA |  |  | 06/17/15 |  | 1
TA | P150263 | SA SEC Evaluation of SAGIA | D |  | Trade & Cmptitvnss | BENHASSINE | Mousley,Peter J. | Saudi Arabia | MNC02 | GTCDR | 03/14/14 | 06/16/14 | A | 06/15/14 | A | 3 | 03/02/15 | A | 03/18/15 | A | 9 | 06/17/15 |  | 12 | 2 | 664.6024 |  | 664.6024 | 863.8532 |  | 863.8532
TA | P143784 | West Africa -- One Stop Border Posts | D |  | Trade & Cmptitvnss | SPEAKMAN | MacWilliam,David Cal | Western Africa | AFCRI | GTCDR | 01/29/13 | 02/12/15 | A | 03/13/13 | A | 1 | 04/15/15 |  | 04/29/15 |  | 25 | 06/17/15 |  | 27 | 1 |  | 234.329 | 234.329 |  | 336.1312 | 336.1312
TA | P131730 | KW CAIT Support Program | D |  | Trade & Cmptitvnss | BENHASSINE | Akeel,Randa | Kuwait | MNC05 | GTCDR | 05/14/12 | 11/12/12 | A | 12/08/12 | A | 6 | 01/29/15 | A | 02/02/15 | A | 25 | 06/17/15 |  | 30 | 4 | 76.9393 |  | 76.9393 | 751.9872 |  | 751.9872
TA | P148944 | Investment promotion for Sverdlovsk reg. | Subtask | P147345 | Trade & Cmptitvnss | ANOS CASERO | Bossoutrot,Sylvie K. | Russian Federation | ECCU1 | GTCDR | 11/26/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/17/15 |  | 18 |  |  |  |  | 46.1097 |  | 46.1097
EW | P147309 | Private Sector Development Policy Notes | J |  | Trade & Cmptitvnss | RASAGAM | Dimitriyev,Steven R. | Comoros | AFCS2 | GTCDR | 08/27/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/18/15 |  | 21 | 0 | 20.4911 |  | 20.4911 | 87.7172 |  | 87.7172
TA | P148338 | Punjab Competitiveness | J |  | Trade & Cmptitvnss | LASAGABASTER | Palmade,Vincent | Pakistan | SACPK | GTCDR | 11/04/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/18/15 |  | 19 | 0 | 159.6401 | 341.049 | 500.6891 | 581.7072 | 341.049 | 922.7563
KP | P154603 | Harnessing Digital Trade | D |  | Trade & Cmptitvnss | SAEZ | Ferrantino,Michael Joseph | World | GTCDR | GTCDR | 01/30/15 |  |  | 03/20/15 | A | 1 |  |  | 06/19/15 |  | 2 | 06/19/15 |  | 2 | 0 | 12.0813 |  | 12.0813 | 12.0813 |  | 12.0813
TA | P133183 | Monitoring Regional Integration Africa | D |  | Trade & Cmptitvnss | RASAGAM | Brenton,Paul | Africa | AFCRI | GTCDR | 11/05/12 | 04/04/13 | A | 02/03/14 | A | 14 | 02/18/15 | A | 03/26/15 | A | 13 | 06/19/15 |  | 16 | 2 | 32.8772 | 157.963 | 190.8402 | 175.4 | 394.2908 | 569.6908
EW | P151750 | Vendor Supplier Diagnostic | D |  | Trade & Cmptitvnss | RASAGAM | Mukim,Megha | Rwanda | AFCE2 | GTCDR | 07/07/14 | 02/27/15 | A | 03/31/15 | A | 8 | 05/15/15 |  | 05/22/15 |  | 1 | 06/22/15 |  | 2 | 1 | 33.217 |  | 33.217 | 33.217 |  | 33.217
EW | P148610 | Informal trade in Maghreb | D |  | Trade & Cmptitvnss | BENHASSINE | Raballand,Gael J. R. F. | Middle East and North Africa | MNARS | GTCDR | 10/28/13 | 11/22/13 | A | 12/04/13 | A | 1 | 11/04/14 | A | 05/25/15 |  | 17 | 06/22/15 |  | 18 | 0 | 36.3018 | 42.6313 | 78.9331 | 108.0301 | 164.2473 | 272.2773
TA | P152054 | SA Support Kafalah SME program | D |  | Trade & Cmptitvnss | BENHASSINE | Abukumail,Ali H. | Saudi Arabia | MNC02 | GTCDR | 07/21/14 | 12/11/14 | A | 01/10/15 | A | 5 |  |  | 06/01/15 |  | 4 | 06/24/15 |  | 5 | 0 | 117.8037 |  | 117.8037 | 117.8037 |  | 117.8037
EW | P154087 | The role of trade in ending poverty | D |  | Trade & Cmptitvnss | SAEZ | Brenton,Paul | World | GTCDR | GTCDR | 01/29/15 | 02/13/15 | A | 03/29/15 | A | 2 | 04/30/15 |  | 05/08/15 |  | 1 | 06/26/15 |  | 2 | 1 | 31.3037 |  | 31.3037 | 31.3037 |  | 31.3037
EW | P131406 | Regional Trade-Health and Education | D |  | Trade & Cmptitvnss | SPEAKMAN | Dihel,Nora Carina | Africa | AFCRI | GTCDR | 08/16/12 | 06/11/13 | A | 12/03/13 | A | 15 | 05/28/15 |  | 06/04/15 |  | 18 | 06/26/15 |  | 18 | 0 |  | 118.4824 | 118.4824 | 15.2829 | 360.0311 | 375.314
KP | P151715 | Policy Note on Air Connectivity | J |  | Trade & Cmptitvnss | HADDAD | Saslavsky,Daniel Mario | Pacific Islands | EACNF | GTCDR | 07/15/14 |  |  |  |  | NA |  |  | 04/28/15 |  |  | 06/26/15 |  | 11 | 1 | 8.3169 |  | 8.3169 | 8.3169 |  | 8.3169
TA | P132367 | Improving Competitiveness NLTA | D |  | Trade & Cmptitvnss | RASAGAM | Dimitriyev,Steven R. | Mauritius | AFCMG | GTCDR | 07/17/12 | 03/06/15 |  | 04/10/15 |  | 32 |  |  | 06/12/15 |  | 2 | 06/26/15 |  | 2 | 0 | 46.3961 |  | 46.3961 | 116.5377 |  | 116.5377
TA | P131613 | Pilot Project for the Promotion of Small | D |  | Trade & Cmptitvnss | RASAGAM | Brenton,Paul | Africa | AFCRI | GTCDR | 06/06/12 | 11/08/12 |  | 11/19/12 | A | 5 | 05/15/15 |  | 05/22/15 |  | 30 | 06/26/15 |  | 31 | 1 |  | 153.3032 | 153.3032 | 3.27 | 264.0135 | 267.2835
EW | P150199 | Oman Economic Diversification Assessment | D |  | Trade & Cmptitvnss | BENHASSINE | Abukumail,Ali H. | Oman | MNC05 | GTCDR | 03/14/14 | 05/14/14 | A | 06/07/14 | A | 2 |  |  | 06/17/15 |  | 12 | 06/29/15 |  | 12 | 0 | 127.85 |  | 127.85 | 153.3719 |  | 153.3719
KP | P154247 | Rethinking SME Policies: Inputs into G20 | D |  | Trade & Cmptitvnss | TILMES | Cusolito,Ana Paula | World | GTCDR | GTCDR | 01/14/15 | 02/13/15 |  | 02/16/15 |  | 1 | 05/22/15 |  | 05/29/15 |  | 3 | 06/29/15 |  | 4 | 1 | 180.6126 |  | 180.6126 | 180.6126 |  | 180.6126
KP | P128882 | New Trade Policy Issues |  |  | Trade & Cmptitvnss | SAEZ | Gillson,Ian John Douglas | World | GTCDR | GTCDR | 09/30/11 | 11/28/11 | A | [8 empty] | 06/29/15 |  |  |  |  | 12.9 | 12.9 | 81.1651 | 12.9 | 94.0651
TA | P147078 | Promoting PPPs in Togo | D |  | Trade & Cmptitvnss | SPEAKMAN | Dia,Magueye | Togo | AFCF2 | GTCDR | 08/02/13 | 05/19/14 | A | 04/17/15 |  | 20 | 06/08/15 |  | 06/15/15 |  | 1 | 06/29/15 |  | 2 | 0 | 6.3351 |  | 6.3351 | 40.9869 |  | 40.9869
TA | P151818 | Africa Sub-regional Growth Triangle | D |  | Trade & Cmptitvnss | RASAGAM | Dimitriyev,Steven R. | Africa | AFCS2 | GTCDR | 06/30/14 | 01/22/15 | A | 04/10/15 |  | 9 |  |  | 06/01/15 |  | 1 | 06/29/15 |  | 2 | 0 | 50.3718 |  | 50.3718 | 50.3718 |  | 50.3718
TA | P126702 | BD: PSDSP - Bank Exec Advisory Services | D |  | Trade & Cmptitvnss | LASAGABASTER | Haththotuwa,Bharatha Manju S. | Bangladesh | SACBD | GTCDR | 05/05/11 | 05/09/11 | A | 07/18/11 | A | 2 |  |  | 05/31/15 |  | 46 | 06/29/15 |  | 47 | 0 | 31.7188 | 254.4693 | 286.188 | 31.7188 | 1374.8265 | 1406.5452
TA | P153576 | EFO Getting electricity in Kaliningrad | Subtask | P147345 | Trade & Cmptitvnss | ANOS CASERO | Bossoutrot,Sylvie K. | Russian Federation | ECCU1 | ECCU1 | 11/14/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/29/15 |  | 7
EW | P153309 | Africa Competitiveness Report 2015 | D |  | Trade & Cmptitvnss | SPEAKMAN | Hoffman,Barak Daniel | Africa | AFRCE | GTCDR | 10/26/14 | 01/22/15 | A | 04/16/15 |  | 5 | 02/27/15 |  | 05/29/15 |  | 1 | 06/30/15 |  | 2 | 1 | 10.7013 | 3.16 | 13.8613 | 10.7013 | 3.16 | 13.8613
EW | P143233 | MG DTIS Update | D |  | Trade & Cmptitvnss | RASAGAM | Hoppe,Mombert | Madagascar | AFCS2 | GTCDR | 03/05/13 | 02/20/14 | A | 03/31/14 | A | 12 | 04/15/15 |  | 04/30/15 |  | 13 | 06/30/15 |  | 15 | 2 | 49.9378 | 79.4049 | 129.3427 | 116.3153 | 81.1342 | 197.4495
EW | P143176 | DTIS Update Guinea | D |  | Trade & Cmptitvnss | SPEAKMAN | Maur,Jean-Christophe | Guinea | AFCF2 | GTCDR | 10/31/12 | 10/07/13 | A | 12/09/13 | A | 13 | 12/17/14 | A | 04/30/15 |  | 16 | 06/30/15 |  | 18 | 2 | 12.2057 | 34.275 | 46.4807 | 12.2057 | 155.1849 | 167.3907
EW | P147986 | Improving National Freight Logistics | Subtask | P146261 | Trade & Cmptitvnss | HADDAD | Rahardja,Sjamsu | Indonesia | EACIF | GTCDR | 09/23/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/30/15 |  | 21 | 0 | 519.6739 |  | 519.6739 | 910.681 |  | 910.681
EW | P149486 | GVCs, Competitiveness, & Integration | Subtask | P148374 | Trade & Cmptitvnss | RASAGAM | Farole,Thomas | Southern Africa | AFCS1 | GTCDR | 01/14/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/30/15 |  | 17 | 2 | 110.7181 | 300.8308 | 411.5488 | 227.6164 | 300.8308 | 528.4472
KP | P154613 | GE Competition Policy | D |  | Trade & Cmptitvnss | SAEZ | Martinez Licetti,Martha | World | GTCDR | GTCDR | 01/30/15 | 03/04/15 | A | 03/10/15 | A | 1 |  |  | 06/19/15 |  | 3 | 06/30/15 |  | 3 | 0 | 0.554 |  | 0.554 | 0.554 |  | 0.554
TA | P154268 | KZ Services Sector Gap Analysis JERP | D |  | Trade & Cmptitvnss | ANOS CASERO | Choi,Jieun | Kazakhstan | ECCU8 | GTCDR | 01/22/15 | 03/17/15 | A | 04/08/15 | A | 2 |  |  | 05/15/15 |  | 1 | 06/30/15 |  | 2 | 1 | 42.3945 |  | 42.3945 | 42.3945 |  | 42.3945
TA | P154907 | Analysis of Effect. of Economy Spprt Msr | D |  | Trade & Cmptitvnss | ANOS CASERO | Choi,Jieun | Kazakhstan | ECCU8 | GTCDR | 02/25/15 | 04/14/15 |  | 04/21/15 |  | 1 | 06/15/15 |  | 06/22/15 |  | 2 | 06/30/15 |  | 2 | 0 | 18.6748 |  | 18.6748 | 18.6748 |  | 18.6748
TA | P153624 | Innovation Grants SME System Support | D |  | Trade & Cmptitvnss | ANOS CASERO | Grigorian,Karen | Kazakhstan | ECCU8 | GTCDR | 01/27/15 | 03/23/15 | A | 03/26/15 | A | 1 |  |  | 06/15/15 |  | 2 | 06/30/15 |  | 3 | 0 | 88.683 |  | 88.683 | 88.683 |  | 88.683
TA | P153871 | Kazakhstan Investment Attraction JERP FY | D |  | Trade & Cmptitvnss | ANOS CASERO | Rekas,Melissa | Kazakhstan | ECCU8 | GTCDR | 12/17/14 | 03/17/15 | A | 03/30/15 | A | 3 | 05/29/15 |  | 06/15/15 |  | 2 | 06/30/15 |  | 3 | 0 | 119.232 |  | 119.232 | 119.232 |  | 119.232
TA | P153893 | Business Regulations Review (RIA) | D |  | Trade & Cmptitvnss | ANOS CASERO | Choi,Jieun | Kazakhstan | ECCU8 | GTCDR | 12/05/14 | 03/03/15 | A | 03/17/15 | A | 3 |  |  | 06/15/15 |  | 2 | 06/30/15 |  | 3 | 0 | 100.1165 |  | 100.1165 | 100.1165 |  | 100.1165
TA | P144731 | Coordinated DPO Southern Africa | D |  | Trade & Cmptitvnss | RASAGAM | Hoppe,Mombert | Africa | AFCRI | GTCDR | 02/06/13 | 07/24/13 | A | 02/05/14 | A | 11 | 05/31/15 |  | 06/05/15 |  | 16 | 06/30/15 |  | 16 | 0 |  | 22.1522 | 22.1522 | 101.6004 | 341.1919 | 442.7923
TA | P147652 | NCBiR Mid Term Eval and TA | D |  | Trade & Cmptitvnss | ANOS CASERO | Kapil,Natasha | Poland | ECCU5 | GTCDR | 09/06/13 | 09/05/13 | A | 10/01/13 | A | 0 | 04/30/15 |  | 05/11/15 |  | 19 | 06/30/15 |  | 20 | 1 | 164.0519 |  | 164.0519 | 334.3974 |  | 334.3974
TA | P150491 | Competition policy capacity building | Subtask | P146625 | Trade & Cmptitvnss | ANOS CASERO | Gonzalez,Alvaro S. | Russian Federation | ECCU1 | GTCDR | 08/27/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 06/30/15 |  | 10
TA | P123177 | Support for Domestic Trade | Subtask | P147042 | Trade & Cmptitvnss | HADDAD | Rahardja,Sjamsu | Indonesia | EACIF | GTCDR | 10/25/10 | 10/25/10 | A | 01/14/13 | A | 26 | 06/17/14 | A | 06/19/14 | A | 17 | 07/02/14 | A | 17 | 0 |  |  |  | 259.698 | 137.9302 | 397.6282
TA | P126842 | Supp. for ID Intl Econ. Engagement-FORA | Subtask | P147042 | Trade & Cmptitvnss | HADDAD | Rahardja,Sjamsu | Indonesia | EACIF | GTCDR | 05/19/11 | 05/23/11 | A | 01/14/13 | A | 19 | 06/14/14 | A | 06/18/14 | A | 17 | 07/02/14 | A | 17 | 0 |  |  |  | 27.4563 | 487.2457 | 514.702
TA | P130986 | Food Security and Commodity Trade | Subtask | P147042 | Trade & Cmptitvnss | HADDAD | Rahardja,Sjamsu | Indonesia | EACIF | GTCDR | 03/19/12 | 08/16/12 | A | 11/20/12 | A | 8 | 06/14/14 | A | 06/19/14 | A | 18 | 07/02/14 | A | 19 | 0 |  |  |  |  | 64.5566 | 64.5566
EW | P132612 | Diagnostic Trade Integration StudyZambia | D |  | Trade & Cmptitvnss | RASAGAM | Dihel,Nora Carina | Zambia | AFCS3 | GTCDR | 08/14/12 | 10/25/12 | A | 03/07/13 | A | 6 | 05/29/14 | A | 06/20/14 | A | 15 | 07/05/14 | A | 15 | 0 |  |  |  | 8.7152 | 377.1376 | 385.8528
EW | P132018 | STP Diagnostic Trade Integration Study | D |  | Trade & Cmptitvnss | SPEAKMAN | Gamberoni,Elisa | Sao Tome and Principe | AFCC1 | GTCDR | 07/19/12 | 11/02/12 | A | 11/20/12 | A | 4 | 09/23/13 | A | 11/04/13 | A | 11 | 07/05/14 | A | 19 | 8 |  |  |  | 16.5954 | 164.8449 | 181.4402
EW | P125131 | Potential Investor Survey | D |  | Trade & Cmptitvnss | SAEZ | Varela,Gonzalo J. | World | GTCDR | GTCDR | 12/03/10 | 10/13/10 | A | 02/10/14 | A | 38 | 04/25/14 | A | 06/13/14 | A | 4 | 07/07/14 | A | 4 | 0 | 12.8324 | 5.8412 | 18.6735 | 154.8462 | 45.6658 | 200.512
TA | P121923 | GLO 2b Agribusiness Incubation Good Prac | D |  | Trade & Cmptitvnss | TILMES | Olafsen,Ellen | World | GTCID | GTCID | 05/06/10 | 05/06/10 | A | 05/29/14 | A | 48 |  |  | 06/05/14 | A | 0 | 07/07/14 | A | 1 | 1 |  |  |  |  | 401.2968 | 401.2968
TA | P147989 | Invest. & Jobs Through Clusters (CIIP) | Subtask | P145769 | Trade & Cmptitvnss | ANOS CASERO | Racine,Jean-Louis Charles | Russian Federation | ECCU1 | GTCDR | 09/24/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 07/09/14 | A | 9 | [5 empty] | 425.9015 | 425.9015
KP | P147703 | Logistics Performance Index 2014 | D |  | Trade & Cmptitvnss | SAEZ | Saslavsky,Daniel Mario | World | GTCDR | GTCDR | 09/11/13 |  |  | 06/30/14 | A | 9 |  |  | 06/30/14 | A | 0 | 07/14/14 | A | 0 | 0 | 16.0057 | 29.4239 | 45.4296 | 207.9719 | 29.4239 | 237.3958
TA | P133236 | RW Policy notes | J |  | Trade & Cmptitvnss | RASAGAM | Fye,Lucy M. | Rwanda | AFCE2 | GTCDR | 11/19/12 | NA |  | NA |  | NA | NA |  | NA |  |  | 07/14/14 | A | 19 | 1 |  |  |  | 350.0703 |  | 350.0703
KP | P144550 | Participation in Innovation Policy Platf | D |  | Trade & Cmptitvnss | TILMES | Dutz,Mark Andrew | World | GTCDR | GTCDR | 01/15/13 |  |  | 01/14/13 |  | 0 |  |  | 06/27/14 |  | 17 | 08/29/14 |  | 19 | 2 |  |  |  | 93.4155 |  | 93.4155
TE | P129863 | EG-Development Marketplace |  |  | Trade & Cmptitvnss | BENHASSINE | Abdel Aziz,Teymour | Egypt, Arab Republic of | MNC03 | GTCDR | 11/30/11 |  | A | 11/23/11 | A | 0 | [5 empty] | 09/11/14 | A | 33 |  |  |  |  | 21.6424 |  | 21.6424
TA | P133074 | CA Regional Conferences | D |  | Trade & Cmptitvnss | KOUAME | Calvo-Gonzalez,Oscar | Central America | LCC2C | GMFDR | 10/10/12 | 04/04/14 | A | 04/04/14 | A | 17 | 05/21/14 |  | 08/20/14 | A | 4 | 09/19/14 | A | 5 | 0 |  |  |  | 147.7723 |  | 147.7723
EW | P143219 | Investment Climate Assessment | D |  | Trade & Cmptitvnss | BENHASSINE | Assaf,Nabila | West Bank and Gaza | MNC04 | GTCDR | 10/03/12 | 10/23/12 | A | 01/29/13 | A | 3 | 04/29/14 | A | 06/27/14 | A | 16 | 09/21/14 | A | 19 | 2 | 29.5097 |  | 29.5097 | 261.1219 |  | 261.1219
KP | P149175 | IC-INTERACTIVE CHILD DEVT | J |  | Trade & Cmptitvnss | TILMES | Devercelli,Amanda Epstein | World | LLIIN | GTCDR | 12/11/13 |  |  |  |  | NA | [5 empty] | 09/30/14 |  | 9 |  |  |  |  | 91.1594 |  | 91.1594
KP | P149200 | IC-TOMORROW'S JOBS | J |  | Trade & Cmptitvnss | TILMES | Iacovone,Leonardo | World | LLIIN | GTCDR | 12/16/13 |  |  |  |  | NA | [5 empty] | 09/30/14 |  | 9 |  | 0.04995 |  | 0.04995 | 98.9511 |  | 98.9511
EW | P144073 | ZW - Competitiveness and Trade Work | D |  | Trade & Cmptitvnss | RASAGAM | Pierola Castro,Martha D. | Zimbabwe | AFCS3 | GTCDR | 01/22/13 | 03/04/13 | A | 05/27/13 | A | 4 | 11/26/13 | A | 08/28/14 | A | 15 | 10/07/14 | A | 16 | 1 |  | 18.4522 | 18.4522 | 18.4514 | 397.8848 | 416.3362
TA | P123763 | T&T - RAS Business Reform (Comp 5) | D |  | Trade & Cmptitvnss | MOTTA | Varada,Sunita | Trinidad and Tobago | LCC3C | GTCDR | 06/01/11 | 08/30/11 | A | 05/12/11 | A | 0 |  |  | 08/22/14 | A | 39 | 10/13/14 | A | 41 | 1 | 35.4851 |  | 35.4851 | 657.0857 |  | 657.0857
EW | P128557 | SO:Political Economy of PSD&Job Creation | D |  | Trade & Cmptitvnss | RASAGAM | Mousley,Peter J. | Somalia | AFCE4 | GTCDR | 10/28/11 | 06/19/12 | A | 09/15/14 | A | 34 | 06/10/14 | A | 10/03/14 | A | 0 | 10/31/14 | A | 1 | 0 | 9.0893 |  | 9.0893 | 192.8105 |  | 192.8105
KP | P149284 | CGE Based Industry Growth Pojections | J |  | Trade & Cmptitvnss | SAGER | Onugha,Ifeyinwa Uchenna | World | FCDKP - HIS | GTCDR | 12/19/13 |  |  |  |  | NA |  |  | 09/14/14 | A |  | 10/31/14 |  | 10 | 1 | 5.5938 |  | 5.5938 | 23.5774 |  | 23.5774
KP | P149180 | IC-MOBILE REVOLVING FUNDS | J |  | Trade & Cmptitvnss | TARALLO | Donna,Christina I. | World | LLIIN | GGODR | 12/11/13 |  |  |  |  | NA | [5 empty] | 11/03/14 | A | 10 |  | 0.22692 |  | 0.22692 | 54.279 |  | 54.279
TA | P145107 | Smart Growth Operational Program Review | Subtask | P145078 | Trade & Cmptitvnss | ANOS CASERO | Kapil,Natasha | Poland | ECCU5 | GTCDR | 03/07/13 | NA |  | NA |  | NA | NA |  | NA |  | 11 | 11/03/14 | A | 19 | 7 | 6.2307 |  | 6.2307 | 194.2056 |  | 194.2056
KP | P148966 | IC-ID MGMT | J |  | Trade & Cmptitvnss | EL-GAMMAL | Koettl - Brodmann,Stefanie | World | LLIIN | GSPDR | 12/11/13 |  |  |  |  | NA | [5 empty] | 11/04/14 | A | 10 |  | 0.132 |  | 0.132 | 108.439 |  | 108.439
KP | P149169 | IC-SIEV PHASE II | J |  | Trade & Cmptitvnss | TILMES | Kanehira,Naoto | World | LLIIN | GTCDR | 12/11/13 |  |  |  |  | NA | [5 empty] | 11/04/14 | A | 10 |  | -0.225 |  | -0.225 | 104.9074 |  | 104.9074
KP | P149178 | IC-URBAN SERVICE MONITORING | J |  | Trade & Cmptitvnss | TILMES | Raich,Uri | Mozambique | LLIIN | GTCDR | 12/11/13 |  |  |  |  | NA | [5 empty] | 11/04/14 | A | 10 |  | 0.66555 |  | 0.66555 | 101.2457 |  | 101.2457
KP | P149181 | IC-SMARTSIGHT | J |  | Trade & Cmptitvnss | TILMES | Soraya,George | World | LLIIN | GTCDR | 12/11/13 |  |  |  |  | NA | [5 empty] | 11/04/14 | A | 10 |  | 0.56491 |  | 0.56491 | 67.0112 |  | 67.0112
KP | P149190 | IC-MOBIL MATERNAL HEALTH | J |  | Trade & Cmptitvnss | BENHASSINE | Holmlund,Marcus E. | World | LLIIN | DECIE | 12/11/13 |  |  |  |  | NA | [5 empty] | 11/04/14 | A | 10 |  |  |  |  | 99.2364 |  | 99.2364
KP | P149192 | IC-CHILD OUTCOMES | J |  | Trade & Cmptitvnss | YAZBECK | Qamruddin,Jumana N. | Madagascar | GHNDR | GHNDR | 12/11/13 |  |  |  |  | NA | [5 empty] | 11/04/14 | A | 10 |  | 3.6595 |  | 3.6595 | 108.5109 |  | 108.5109
KP | P149208 | IC-E-SCIENCE ED | J |  | Trade & Cmptitvnss | TILMES | Parajuli,Dilip | Bangladesh | LLIIN | GTCDR | 12/16/13 |  |  |  |  | NA | [5 empty] | 11/04/14 | A | 10 |  | 0.00443 |  | 0.00443 | 103.0931 |  | 103.0931
KP | P149210 | IC-WATER BILLS | J |  | Trade & Cmptitvnss | TILMES | Vargas-Ramirez,Miguel | World | LLIIN | GTCDR | 12/16/13 |  |  |  |  | NA | [5 empty] | 11/04/14 | A | 10 |  | -3.4161 |  | -3.4161 | 45.2921 |  | 45.2921
TA | P146494 | Private Sector Development TA | D |  | Trade & Cmptitvnss | ANOS CASERO | Reis,Jose Guilherme | Turkey | ECCU6 | GTCDR | 07/12/13 | 10/10/13 | A | 11/04/13 | A | 3 | 09/30/14 | A | 09/30/14 | A | 10 | 11/12/14 | A | 12 | 1 | 12.9499 |  | 12.9499 | 219.6433 |  | 219.6433
KP | P149194 | IC-DISPLACED HOUSING | J |  | Trade & Cmptitvnss | TILMES | Hamilton,Ellen | World | LLIIN | GTCDR | 12/11/13 |  |  |  |  | NA | [5 empty] | 11/19/14 |  | 11 |  | 3.0343 |  | 3.0343 | 98.1313 |  | 98.1313
TE | P125922 | CMI-IT: Financing Services to Innovators |  |  | Trade & Cmptitvnss | BENHASSINE | Uhlmann,Janette | Middle East and North Africa | MNCMI | MNCMI | 02/22/11 |  | A | 03/01/11 | A | 0 | [5 empty] | 11/26/14 | A | 44 |  |  |  |  | 46.6345 | 17.7614 | 64.3958
TA | P149013 | TN: Advancing Global Integration | J |  | Trade & Cmptitvnss | BENHASSINE | Marotta,Daniela | Tunisia | MNC01 | GTCDR | 12/18/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 11/30/14 | A | 11 | 1 | 7.1099 | 4.4232 | 11.5331 | 57.953 | 47.8675 | 105.8204
EW | P145798 | Sudan DTIS Update | D |  | Trade & Cmptitvnss | RASAGAM | Geiger,Michael Tobias | Sudan | AFCE4 | GTCDR | 05/02/13 | 01/10/14 | A | 02/05/14 | A | 9 | 06/19/14 | A | 11/17/14 | A | 9 | 12/02/14 | A | 9 | 0 | 8.5054 | 47.0966 | 55.6019 | 28.3351 | 187.6702 | 216.0053
EW | P133072 | Chad Value Chain Study and Analysis | J |  | Trade & Cmptitvnss | SPEAKMAN | Hayatou,Mohamadou S | Chad | AFCW3 | GTCDR | 10/18/12 | NA |  | NA |  | NA | NA |  | NA |  |  | 12/02/14 | A | 25 | 6 | 2.925 |  | 2.925 | 162.9432 |  | 162.9432
TA | P148087 | TKM WTO Accession | D |  | Trade & Cmptitvnss | ANOS CASERO | Gyulumyan,Gohar | Turkmenistan | ECCU8 | GTCDR | 12/30/13 | 03/11/14 | A | 05/29/14 | A | 4 | 06/25/14 | A | 09/18/14 | A | 3 | 12/02/14 | A | 6 | 2 | 0.51794 |  | 0.51794 | 35.5202 |  | 35.5202
TA | P148486 | Business Environment Dialogue | Subtask | P147637 | Trade & Cmptitvnss | ANOS CASERO | Salinas Munoz,Emanuel | Turkmenistan | ECCU8 | GTCDR | 10/22/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 12/02/14 | A | 13 | 0 | 0.15367 |  | 0.15367 | 19.7046 |  | 19.7046
TA | P148488 | Privatization Dialogue | Subtask | P147637 | Trade & Cmptitvnss | ANOS CASERO | Salinas Munoz,Emanuel | Turkmenistan | ECCU8 | GTCDR | 10/22/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 12/02/14 | A | 13 | 0 | 1.6655 |  | 1.6655 | 34.8264 |  | 34.8264
EW | P132934 | The Private Sector and Job Creation | D |  | Trade & Cmptitvnss | RASAGAM | Garcia,Andres F. | South Sudan | AFCE4 | GTCDR | 08/28/12 | 12/19/12 | A | 01/18/13 | A | 4 | 09/16/14 | A | 11/03/14 | A | 21 | 12/07/14 | A | 22 | 1 |  |  |  | 213.9344 |  | 213.9344
PA | P147042 | Improving Domestic and Intl Trade | NA |  | Trade & Cmptitvnss | HADDAD | Rahardja,Sjamsu | Indonesia | GTCDR | GTCDR | 08/12/13 | 08/26/13 |  | 08/26/13 | A | 0 |  |  | NA |  |  | 12/08/14 | A | 15
KP | P128951 | Border Management Implementation Toolkit |  |  | Trade & Cmptitvnss | SAEZ | McLinden,Gerard | World | GTCDR | GTCDR | 10/03/11 | 10/05/11 | A | [8 empty] | 12/16/14 | A |  |  | 72.6128 |  | 72.6128 | 549.9316 | 5.4752 | 555.4067
TA | P145109 | Smart Specialization (RIS3) Review | Subtask | P145078 | Trade & Cmptitvnss | ANOS CASERO | Piatkowski,Marcin | Poland | ECCU5 | GTCDR | 03/18/13 | NA |  | NA |  | NA | NA |  | NA |  | 3 | 12/16/14 | A | 20 | 16 | 1.9546 |  | 1.9546 | 193.7353 |  | 193.7353
PA | P147637 | TM FSD/PSD Dialogue | NA |  | Trade & Cmptitvnss | ANOS CASERO | Salinas Munoz,Emanuel | Turkmenistan | ECCU8 | GTCDR | 09/18/13 | 09/27/13 | A | 10/01/13 | A | 0 |  |  | NA |  |  | 12/17/14 | A | 14 |  | 22.1059 |  | 22.1059 | 115.9094 |  | 115.9094
TA | P148496 | NQI Readiness Analytical Framework | Subtask | P147505 | Trade & Cmptitvnss | ANOS CASERO | Salinas Munoz,Emanuel | Central Asia | ECCU8 | GTCDR | 10/23/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 12/17/14 | A | 13 | 0 |  |  |  | 17.2406 |  | 17.2406
TA | P148497 | PILOT NQI Analytical Framework | Subtask | P147505 | Trade & Cmptitvnss | ANOS CASERO | Salinas Munoz,Emanuel | Central Asia | ECCU8 | GTCDR | 10/25/13 | NA |  | NA |  | NA | NA |  | NA |  |  | 12/17/14 | A | 13 | 0 |  |  |  | 6.3367 |  | 6.3367
TA | P150577 | PF Sector / Project Briefs | Subtask | P147320 | Trade & Cmptitvnss | MOTTA | Reddy,Rekha | Panama | LCC2C | GTCDR | 05/05/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 12/20/14 | A | 7 |  |  |  |  | 8.0615 |  | 8.0615
TA | P152429 | Conference on Competitiveness | J |  | Trade & Cmptitvnss | ANOS CASERO | Salinas Munoz,Emanuel | Turkmenistan | ECCU8 | GTCDR | 09/04/14 | NA |  | NA |  | NA | NA |  | NA |  |  | 12/24/14 | A | 3 | 1 | 117.3782 |  | 117.3782 | 117.3782 |  | 117.3782
EW | P126672 | KH-Investment Climate Assessment (ICA) 3 | D |  | Trade & Cmptitvnss | HADDAD | Clarke,Julian Latimer | Cambodia | EACTF | GTCDR | 05/05/11 | 08/11/11 | A | 03/11/11 | A | -1 | 05/22/14 | A | 08/05/14 | A | 40 | 12/31/14 | A | 45 | 4 |  | 26.4573 | 26.4573 |  | 372.4401 | 372.4401
Total |  | 202 | [9 empty] | 122 |  | 121 |  |  | 66 |  | 69 |  |  | 81 |  |  |  | 7136.5904 | 7291.4326 | 14428.023 | 28139.9056 | 41644.7997 | 69784.7053